## Import
Type | World | Area | Title | Description | Due date (YYYY-MM-DD) | Project | Rock | Status | Tags
World |  |  | 19Keys | Everything run for 19Keys as his manager and integrator.
Area | 19Keys |  | Supermind
Rock | 19Keys | Supermind | Launch the Supermind affiliate program | Program live with 25 active affiliates and tracked payouts. | 2026-12-15 |  |  | on | revenue
Project | 19Keys | Supermind | Affiliate program build | Terms, tracking links, onboarding page. | 2026-11-15 |  | Launch the Supermind affiliate program | open | build
Project | 19Keys |  | Weekly operating rhythm | Standing meeting agenda and follow-ups. No date, so Orí shows it as Ongoing. |  |  |  | open | ops
To-Do | 19Keys | Supermind | Send affiliate terms to legal review |  | 2026-09-30 | Affiliate program build | Launch the Supermind affiliate program |  | legal
To-Do | 19Keys | Supermind | Pick the payout platform | Dated past 14 days and linked to a Rock, so Orí imports it as a checkpoint. | 2026-10-20 | Affiliate program build | Launch the Supermind affiliate program
Issue | 19Keys | Supermind | Flat commission or tiered commission? | Decide before the terms go out. |  | Affiliate program build
Note | 19Keys | Supermind | Affiliate positioning | Lead with the ritual, not the discount. |  |  |  |  | brand

## How to fill it in
Orí Import Template
How to use | Delete the purple example rows on the Import tab, add one row per record, then File → Save As → CSV. In Orí: Settings → Import → Upload completed CSV.
Order | Rows can be in any order. Orí creates Worlds first, then Areas, Rocks, Projects, and the rest, so links always resolve.
Column | What goes in it
Type | World, Area, Rock, Project, To-Do, Issue or Note.
World | The World this record lives in. Leave blank only on World rows. Must match a World name exactly.
Area | Optional. An ongoing line of work inside the World. Area rows need only Type, World and Title: no dates, no description.
Title | The name of the record. Required on every row.
Description | Optional detail. For a Rock, write the finish line so anyone could tell when it is done.
Due date | YYYY-MM-DD. Required for Rocks. Optional for Projects (blank shows as Ongoing). To-Dos may be dated up to 14 days out; a later To-Do linked to a Rock becomes a checkpoint.
Project | Optional. The exact Title of a Project in the same World.
Rock | Optional. The exact Title of a Rock in the same World.
Status | Rocks: on or off. Projects: open or completed. Other types: leave blank or use completed.
Tags | Optional. Separate tags with semicolons, for example: build;site. Tags let one record show up in filters across Worlds.
Rules Orí enforces | Up to 10 Worlds. Up to 3 active Rocks per World; extra Rocks wait in that World's queue. Names that link rows (World, Area, Project, Rock) must match exactly.